Statement of Work

## Introduction

Name of Project

Aya Healthcare Analyzer Tool

| Contact | Email/Cell |
| --- | --- |
| Sponsor: | Customer.healthcare@aya.com |
| Stakeholder: | Aya Partner (Clinical Operations Director) |
| Project Manager: | Ravi Gude |
| Team Member: | Sai Karthikeya (Lead Developer) |
| Contractor/Vendor: | Brent Wallace (QA Specialist) |

Background

Healthcare staffing involves managing hundreds of Statements of Work (SOWs) with different hospitals. Each SOW contains complex details about compliance, billing rates, and contract terms. Currently, the operations team manually reviews these documents, a process that is time-consuming, prone to human error, and delays the identification of contractual issues.

Purpose

To eliminate manual effort and reduce errors by developing the Aya Healthcare Analyzer Tool. This tool will automatically parse SOW documents, extract key data points, and present them in an intuitive dashboard. This will allow stakeholders to instantly visualize pain points (e.g., below-market rates, strict compliance deadlines) and make faster, data-driven decisions.

## Scope of Work

| To Be Done | Resources Needed | Outcome | Time Involved | General Steps |
| --- | --- | --- | --- | --- |
| OCR & Data Extraction: Develop a module to extract text from uploaded PDF SOWs. | Python script using libraries like pdfplumber / pytesseract. | Raw text extracted from documents with 95% accuracy. | 3 Weeks | 1. Setup environment. 2. Implement PDF parser. 3. Test with 10 sample SOWs. |
| NLP & Logic Analysis: Use Natural Language Processing to identify key clauses (rates, compliance, termination). | Access to OpenAI API / Hugging Face models; Development time for Sai. | System flags "pain points" like rates 10% below average or missing compliance deadlines. | 4 Weeks | 1. Define data schema. 2. Train/configure NLP model. 3. Build logic engine for flagging issue |
| Dashboard Visualization: Create a front-end dashboard to display analyzed data and issues. | React.js frontend; Power BI integration; UI/UX design input. | Interactive dashboard showing contract health, issue summaries, and key metrics. | 3 Weeks | 1. Design wireframes. 2. Build UI components. 3. Connect to backend API. |

## Location

| Site | Duration |
| --- | --- |
| Office | Powell, Ohio (Hybrid - Tuesdays & Thursdays) |
| Remote Location | Home offices (Mon, Wed, Fri) |

## Schedule

| Phases | Start | Finish |
| --- | --- | --- |
| Discovery & Design | 2026-03-01 | 2026-04-30 |
| Development (Sprints 1-3) | 2026-05-01 | 2026-06-29 |
| Testing & UAT | 2026-07-01 | 2026-11-01 |

## Deliverables

| Deliverable | Objective | Due Date |
| --- | --- | --- |
| Deliverable #1 | Project Charter & Wireframes: High-level scope and visual mockups of the dashboard. | 2026-05-15 |
| Deliverable #2 | Functional Prototype: A working version of the tool that can parse at least one SOW type and display data in a test environment. | 2026-06-20 |
| Deliverable #3 | Final Tool & Documentation: Production-ready tool with user manual and technical documentation. | 2026-07-20 |

## Milestones

| Milestones | Start Date | Finish Date |
| --- | --- | --- |
| Milestone #1 | Architecture Sign-off: Core tech stack and database design approved by Ravi. | 2026-05-10 |
| Milestone #2 | Extraction Engine Complete: Sai confirms the tool can successfully read 100% of test PDFs. | 2026-06-10 |
| Milestone #3 | UAT Sign-off: Stakeholder ("Aya Partner") signs off that the dashboard meets business needs. | 2026-07-16 |

## Tasks

| Activity | Team Member | Duration |
| --- | --- | --- |
| Backend API Development: Build the REST API to handle file uploads and serve data to the frontend. | Sai | 3 weeks |
| Frontend Dashboard Development: Code the React components for the "Issues Overview" and "Contract Details" pages. | Gagan | 5 weeks |
| QA & Validation: Test the tool against 50 historical SOWs to ensure accuracy and report bugs. | Brent | 3 weeks |

Reporting and Communications

- Daily Stand-up: 15-minute meeting via Microsoft Teams every morning at 9:30 AM to discuss progress, blocks, and priorities. - Sprint Reviews: Bi-weekly demo to the Stakeholder showing the completed work for the sprint. - Status Reporting: Ravi will send a concise email update every Friday by 4:00 PM EST, summarizing progress against milestones, risks, and next steps.

## Standards and Testing

| Standard/Test | Team Member | Due Date |
| --- | --- | --- |
| Standard | Sai | 2026-03-10 |
| Test #1 | Gagan | 2026-05-10 |
| Test #2 | Brent | 2026-07-10 |

## Define Success

The stakeholders and sponsor deem the project successful when: - The tool reduces the time spent analyzing a single SOW from an average of 45 minutes to under 5 minutes. - The dashboard successfully identifies and visualizes the top 3 "pain points" defined in the requirements.

## Requirements

- Equipment: Developer access to Aya's cloud sandbox environment (AWS/Azure). Standard issue laptops with 16GB+ RAM for developers. - Degrees/Certification: No specific certifications required, but experience with React, Python, and cloud services is mandatory. - Travel: No travel is required for this project.

## Other

- Success Criteria: The tool should be designed to scale. While we are starting with PDF SOWs, the architecture should allow for future integration with email parsing or direct CRM connections. - Training: Upon closure, Sai will conduct a 1-hour "Train the Trainer" session for the Stakeholder to enable internal knowledge transfer.

## Payments

| Who | How Much | Payment Due |
| --- | --- | --- |
| Dev Resource | $50,000 | Upon Completion (Full) |
| QA Resource | $15,000 | Upon Completion (Full) |
| Cloud Credits | $5000 | As Incurred |

## Closure

| Document | Signed Off |
| --- | --- |
| Doc #1 | Final Code Repository Handover |
| Doc #2 | User Training Completion Form |
| Doc #3 | Final Project Sign-off (Sponsor Approval) |