SOA INTEGRATION SERVICES

FOR PROJECT PAYMENT PROCESSING COMPANY 

Statement of Work

Abstract

Providing in scope SOA Integration services for PAYMENT PROCESSING COMPANY Project to CLIENT-1, leveraging qualified project staff and technical experts with relevant project experience, delivering within fixed budget.

SEPTEMBER 7, 2023

Table of Contents

About Us	3

Organizational history and structure	3

Years in business providing technical consulting and programming service(s)	3

Project Description	4

Scope of the project	4

Deliverables and Estimated Efforts	5

Project Timeline	6

Resource Structure	7

Assumptions	7

Payments Schedule	8

Standard Terms	8

# Version History

| Version | Date | Created or modified by | Comments |
| --- | --- | --- | --- |
| Initial Version | 09/11/2023 | Ravi Gude | Initial Proposal |
| V1 | 09/15/2023 | Ravi Gude | As per Harold’s suggestion moved CLIENT-1SIP enhancements as Milestone 1 |
| V2 | 09/202023 | Ravi Gude | Added additional content for each milestone in the deliverables |
| V3 | 09/21/2023 | Ravi Gude & Naga Nannapaneni | Reviewed and matched the scope and deliverable items sections |
| V4 | 09/29/2023 | Ravi Gude & Naga Nannapaneni | Changed the acceptance criteria as per Harold’s suggestion |
| Final | 10/03/2023 | Ravi Gude & Naga Nannapaneni | Reviewed the final version with Harold via Teams Call |

# About Us

Ocean Blue Solutions Inc. stands at the forefront of the IT consulting and programming services industry, tailoring professional IT solutions to address a broad spectrum of business requirements. With a demonstrated history of executing successful projects in domains like data management life cycle, cloud computing, cyber security, and beyond, we bring a wealth of experience to every client. Our team comprises adept and seasoned IT professionals with the essential expertise, tools, and technology to fulfill all contractual obligations with excellence.

Ocean Blue Solutions Inc. provides comprehensive Oracle services utilizing a blend of onshore and offshore resources. This approach leads to cost savings and ensures that you receive the requisite expertise and support. Our team consists a diverse skill set encompassing architecture, development, and support. Our resources are well-equipped to handle legacy and modern applications and are proficient in various technologies, including Oracle R12 & Cloud, SOA, OIC, SAP, and others.

### Organizational history and structure

Founded in 2013, Ocean Blue Solutions is a Professional Technology Services firm that delivers high-quality solutions to solve our clients' Workforce challenges. We use an onsite/offshore model that is flexible and cost-effective.

### Years in business providing technical consulting and programming service(s)

OceanBlue Solutions is a technical consulting and programming services company that has been serving the Columbus metropolitan area for more than a decade. We have successfully delivered projects for clients in the Manufacturing and Healthcare sectors. Our team consists of skilled project managers, developers, Team Leads, SMEs, and support staff who collaborate to ensure timely, budget-friendly, and quality outcomes. We also have a quality assurance process to test and verify all work according to the clients’ specifications.

Our Philosophy:  
At Ocean Blue, our seasoned experts hail from diverse sectors and fields. When engaging with a new client, we adopt a genuine partnership approach. We believe in seamlessly integrating the Ocean Blue team with our clients, rather than functioning as an external entity, to elevate the collaborative experience.

# Project Description

This document provides a proposal for adding a new CLIENT-1SIP connection to PAYMENT PROCESSING COMPANY, and design/build new SOA Integration services complementing the current CLIENT-1SIP environment to meet Diebold Nixdorf and PAYMENT PROCESSING COMPANY requirements. Brief summary of the project as follows:

- Build the CLIENT-1SIP Integrations for PAYMENT PROCESSING COMPANY that will add PAYMENT PROCESSING COMPANY to the exist CLIENT-1SIP platform.

- Build the new enhancements required for the project

  - SOA Attachments integrations

  - Invoice publishing service

  - Invoice approval process

- The integrations will be built using SOA v12, and the invoice publishing service will be built in Oracle R12. Diebold Nixdorf maintains 4 environments in their Production track for Oracle R12 and Oracle SOA middleware, they are DEV, SIT, UAT and PROD.

Nonfunctional Requirements:

- CLIENT-1 retains the intellectual property rights to the finished product

- Solution needs to be scalable, updatable, and adaptable in order to meet future business, regulatory, and technology needs

# Scope of the project

The scope of the project involves 5 SOA integrations and one CLIENT-1SIP enhancement as outlined below:

Milestone 1: Deliver Project design, build PAYMENT PROCESSING COMPANY CLIENT-1SIP connection, and deploy CLIENT-1SIP connection to Production

- CLIENT-1SIP Integration with PAYMENT PROCESSING COMPANY for work orders

- Outbound

- Inbound

* Clone the existing CLIENT-1SIP Integration and modifying as per PAYMENT PROCESSING COMPANY mapping requirements.

* Inbound and Outbound Control tables remain same

Milestone 2: Design a process to allow CLIENT-1SIP to send and receive attachments

- Integration # 1 – Retrieve the attachments from CLIENT-1 Hadoop environment under the SR Number and send them to PAYMENT PROCESSING COMPANY

  - Built as part of the CLIENT-1SIP process for call closure. Will work for all future customers requesting to receive attachments from CLIENT-1 SR’s

- Integration # 2 – Receive attachments from PAYMENT PROCESSING COMPANY and save it to CLIENT-1 Hadoop environment under the SR Number

  - Built as part of the CLIENT-1SIP process for call creation. Will work for all future customers sending attachments on CLIENT-1 SR’s. These attachments would likely be instructions that a tech needs to see and as part of their repair task. This integration requires a methodology to notify and allow the tech to view the attachment.

Milestone 3: Design a method to compliment the current invoicing & billing processes to better provide the PAYMENT PROCESSING COMPANY invoiced approval status.

- Integration # 3 – VENDOR WO BILLING PREAPPROVAL REQUEST * May need to work with other teams to create a webservice to display the invoices that needs to be pre-approval. Refer to the existing process.

  - Review the call closing activities for a given SR and flag for PAYMENT PROCESSING COMPANY approval 
for invoicing

  - Build a parking lot to store invoices that need to be preapproved. Write a SOA integration to pick up the Invoices from the Oracle R12 queue and populate the parking lot with the invoice data. Build API/process that allows PAYMENT PROCESSING COMPANY to send invoice acceptance updates to the parking lot (approved, denied, etc.). Depending on investigation during functional requirements additional processes will be identified to assist finance in the special handling of the invoice. This could be various types of reporting or similar type of automation from the parking lot. This would not include any modifications to the actual billing/invoicing process. CLIENT-1 may create a webservice to provide information to invoicing team to help reduce the additional effort that may be introduced.

- Integration # 4 – Retrieve PAYMENT PROCESSING COMPANY Invoices from Oracle R12 EBS2 Write Oracle R12 code to publish PAYMENT PROCESSING COMPANY invoices to a queue using a canonical model. Requires queues to be built and process to trigger the updating of the queue.

- Integration # 5 – Send invoices to PAYMENT PROCESSING COMPANY

  - Design the Billing pre-approval process to avoid sending the invoices to PAYMENT PROCESSING COMPANY without their approval on closed SR

  - Design a process to send Billing data to PAYMENT PROCESSING COMPANY, once the SR is approved for invoicing by PAYMENT PROCESSING COMPANY.

  - Retrieve invoices from a database parking lot and send them to PAYMENT PROCESSING COMPANY via a SOA integration calling PAYMENT PROCESSING COMPANY API.  This may require translating billing code from CLIENT-1 to PAYMENT PROCESSING COMPANY. This would be done via a DVM/Lookup table.

# Deliverables and Estimated Efforts

The project scope has been segmented into the following phases, each with specific deliverables requiring client approval to progress to the next phase. The effort estimates provided are preliminary and based on current available information at the time of this SOW. These estimations will be thoroughly reassessed once detailed requirements are finalized, and the technical design is confirmed.

| Phase | Estimated Efforts | Acceptance Criteria |
| --- | --- | --- |
| Requirement Elicitation and Connectivity with Vendor | 4 weeks | Detailed Requirements Document |
| Technical Design | 2 weeks | Technical Design Document |
| Development: |  |  |
| Milestone 1: |  |  |
| CLIENT-1SIP Integration with PAYMENT PROCESSING COMPANY for work orders - Outbound - Inbound * Clone the existing CLIENT-1SIP Integration and modifying as per PAYMENT PROCESSING COMPANY mapping requirements. * Inbound and Outbound Control tables remain same | 4 weeks | SOA Component development, Unit test, SIT, UAT and business sign-off complete |
| Milestone 2: |  |  |
| Integration 1 – Retrieve the attachments from CLIENT-1 Hadoop environment under the SR Number and send them to PAYMENT PROCESSING COMPANY | 5 weeks | SOA Component development, Unit test, SIT, UAT and business sign-off complete |
| Integration 2 – Receive attachments from PAYMENT PROCESSING COMPANY and save it to CLIENT-1 Hadoop environment under the SR Number | 5 weeks | SOA Component development, Unit test, SIT, UAT and business sign-off complete |
| Milestone 3: |  |  |
| Integration 3 – VENDOR WO BILLING PREAPPROVAL REQUEST * May need to work with other teams to create a webservice to display the invoices that needs to be pre-approval. Refer to the existing process. | 6 weeks | SOA Component development, Unit test, SIT, UAT and business sign-off complete |
| Integration 4 – Retrieve PAYMENT PROCESSING COMPANY Invoices from Oracle R12 EBS2 | 4 weeks | SOA Component development, Unit test, SIT, UAT and business sign-off complete |
| Integration 5 – Send invoices to PAYMENT PROCESSING COMPANY Billing Process - Pre-Approval and Billing Data to PAYMENT PROCESSING COMPANY | 6 weeks | SOA Component development, Unit test, SIT, UAT and business sign-off complete |
| System Integration testing (SIT) | 2 weeks | SIT Sign Off |
| UAT | 3 weeks | UAT Sign Off |
| Production Migration | 1 week | PROD Sign off |
| Hypercare | 6 weeks | Close all High/Critical BUGs |
| Knowledge Transfer | 1 week | KT Documents |

# Project Timeline

Our delivery approach ensures a systematic and controlled progression from understanding client needs (requirements gathering) to the actual design, development, implementation, and verification of the solution in the production environment. It allows for a systematic and organized project execution, reducing the risk of errors and ensuring that the final product aligns closely with the client's expectations.

Ocean Blue project manager will collaborate closely with the CLIENT-1 IT team to refine and finalize the detailed project plan on a monthly basis.

The diagram below offers a broad, top-level view of our proposed project plan:

| WBS (Work Breakdown Structure) | Oct-23 | Nov-23 | Dec-23 | Jan-24 | Feb-24 | Mar-24 | Apr-24 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Team onboarding |  |  |  |  |  |  |  |
| Requirement Elicitation and Connectivity with Vendor |  |  |  |  |  |  |  |
| Design |  |  |  |  |  |  |  |
| Development |  |  |  |  |  |  |  |
| CLIENT-1SIP Enhancement - Receive Attachments |  |  |  |  |  |  |  |
| Integration 1 – VENDOR WO ATTACHMENTS |  |  |  |  |  |  |  |
| Integration 2 – FSP2VF_FILE_DOWNLOAD |  |  |  |  |  |  |  |
| Integration 3 – VENDOR WO BILLING PREAPPROVAL REQUEST |  |  |  |  |  |  |  |
| Integration 4 – VENDOR INVOICE UPDATE |  |  |  |  |  |  |  |
| Integration 5 – Billing Process - Pre Approval and Billing Data to PAYMENT PROCESSING COMPANY |  |  |  |  |  |  |  |
| System testing (SIT) |  |  |  |  |  |  |  |
| User Acceptance Testing (UAT) |  |  |  |  |  |  |  |
| Production Migration |  |  |  |  |  |  |  |
| Hypercare |  |  |  |  |  |  |  |
| Knowledge Transfer |  |  |  |  |  |  |  |

# Resource Structure

This section outlines the technical roles necessary for successful project execution. If the project is awarded to Ocean Blue Solutions, we will select skilled professionals, technologies, and equipment to successfully deliver the project. This may include roles such as project manager, developers, designers, and QA testers, along with any specialized software or hardware required. Once finalized, we will share the experience and expertise of the team members with CLIENT-1, to demonstrate their suitability for the project. Listed below are the preliminary role types from the team who will handle the project tasks.

We anticipate below resources are required to execute the project outlined in this proposal.

| S.No | Role | Resource Count | Allocation % |
| --- | --- | --- | --- |
| 1 | Business Analyst | 1 | 100% |
| 2 | SOA Developers | 2 | 100% |
| 3 | Project Manager | 1 | 40% |
| 4 | Oracle R12 | 1 | 20% |

# Assumptions

- There will be no delays to project schedule from PAYMENT PROCESSING COMPANY and CLIENT-1 in finalizing the requirements and testing as delays will impact timelines and the scope that can be delivered within the budget.

- There is an existing B2B integration in place, so no new development is involved for B2B within the scope of this project

- Any potential downtime with CLIENT-1SIP or other CLIENT-1, PAYMENT PROCESSING COMPANY Systems will impact this project’s timeline and deliverables, other than planned non prod outages needed for monthly patching activities.

- A new change request (CR) will be submitted for the extra effort and any associated costs, if there is a change in scope of this project

- Any project delays caused by events outside of Ocean Blue Solution’s purview may need adjustments to the timeline and/or scope of this project

- There will be technical support from Hadoop, CLIENT-1SIP, PAYMENT PROCESSING COMPANY and any other systems to integrate through SOA.

# Payments Schedule

Ocean Blue Solutions will issue invoices based on the following schedule upon completing each designated milestone or deliverable successfully. This structured approach ensures billing aligns with project progress, providing transparency and accountability for both parties.

| Phase | % Billed | Amount (USD) |
| --- | --- | --- |
| Requirements, Technical Design and Development - Milestone 1 completion | 25% | 47,250 |
| Development - Milestone 2 completion | 15% | 28,350 |
| Development - Milestone 3 completion | 15% | 28,350 |
| SIT Completion | 15% | 28,350 |
| Post GO-LIVE | 20% | 37,800 |
| End of Hypercare | 10% | 18,900 |
| TOTAL | 100% | 189,000 |

# Standard Terms

Ocean Blue Solutions agrees that no information will be disclosed to third parties or published in case studies, advertisements, white papers, customer testimonials, etc. without the written consent of CLIENT-1.

Confidentiality: Ocean Blue Solutions holds a position of trust with the information received during performance of work under the Contract. We recognize the responsibility entrusted to us for preserving the security and confidentiality of such information. CLIENT-1 has determined that information it treats as confidential may be disclosed to us in the performance of its work under the Contract. Therefore, we agree to the following.

CLIENT-1 may disclose to Ocean Blue Solutions Inc., data or other information that CLIENT-1 treats as confidential. Title to the Confidential Information and all related materials and documentation CLIENT-1 delivers to us will remain with CLIENT-1. We treat such Confidential Information as secret if it is so marked, otherwise identified as such, or when, by its very nature, it deals with matters that, if generally known, would be damaging to the best interests of the public, other contractors or potential contractors with CLIENT-1, or individuals or organizations about whom CLIENT-1 keeps information. Information will be treated as confidential if it includes any information expressly excluded by Ohio law from public records disclosure requirements.

ACCEPTED:

client				OceanBlue Solutions, Inc.

n

By: _________________________________			By: ________________________

(Authorized Signature)							(Authorized Signature)

Name: ______________________________			Name: ______________________

Title: _______________________________			Title: ________________________

Date: _______________________________			Date: _______________________